## RACI - CATS
R=Responsible, A=Accountable, C=Consulted, I=Informed
Domain | Task | CAGIP UNIX BUILD | SUL SYS | CAGIP STKG BUILD
CATS Storage Migration (VPLEX Invista --> PMAX Symmetrix) | Change creation for Prod Servers | R | I | I
| CAB Approvals for the Change created | R | I | -
| Change task for Run team | A | C | -
| Application Team's Approvals regarding downtime for Server reboots | R,A | A,I | -
| LUN Assignment | A,C | I | R
| SMTT job schedule to be shared to Run team | R | I | -
| List of Servers in scope (Exhaustive list of Prod,Hors-Prod) | R,A | C,I | C,I
| Any new procedures for Db2 or Db2-HADR Clusters | R | I | I
| Lun Reclaim | C | A | R